## Team Backlog
Team Backlog
Task Name | Assignee | Task Status | Expected Time to Finish (Hrs) | Actual Time to Finish (Hrs)
Design
High Level Design
Modules' Description | All Team | Done | 1 | 1
Drivers' Documentation | All Team | Done | 1 | 1
Low Level Design
Functions' Flowchart | All Team | Done | 2 | 2
Summary
Document File | Hossam | Done | 1 | 2
Implementation
MCAL Module
GPIO Driver | Alaa | Done | 0.5 | 1
SYSTICK | Hossam | Done | 1 | 1.5
HAL Module
BTN Driver | Alaa | Done | 1 | 1
LED | Hossam | Done | 0.5 | 0.5
APP Module
App Driver | Hossam | Done | 1 | 2
Testing
Documentation
Test Protocol Excel Sheet | All Team | Done | 1 | 1
Unit Testing
Test MCAL | All Team | Done | 2 | 2
Test HAL | All Team | Done | 1 | 1
System Testing
Test APP | All Team | Done | 1 | 1
Final Requirements Review | All Team | Done | 1 | 1
Video
Video Recording | All Team | Done | 1 | 2
Video Editing / Upload | Hossam | Done | 1 | 1

## Test Protocol
Test Protocol
Test Case ID | Test Case Description | Test Case Steps | Expected Result | Actual Result | Pass/Fail
APP Module
App Testing
TC_APP_001 | Initial state test | 1. Flash the program hex file 2. Press Reset Switch 3. Do Nothing more | Expected to have all the RGB LEDs off | Matches Expected Result | Pass
TC_APP_002 | SW1 Button presses | 1. Flash the program hex file 2. Press Reset Switch 3. Press the switch SW1 button multiple times sequentially and note down the result per each press | Expected for each button press the following results should occur sequentially: 1st Press: RED LED only is ON for one second only 2nd Press: GREEN LED only is ON for one second only 3rd Press: BLUE LED only is ON for one second only 4th Press: All RGB LEDs are on (white light is produced) for one second only 5th Press: All RGB LEDs are off (no light) 6th Press: Repeat from "1st press" step | Matches Expected Result | Pass
TC_APP_003 | SW1 Button is pressed during LED on time (1s) | 1. Flash the program hex file 2. Press Reset Switch 3. Press the switch SW1 button 1 time, red LED will turn on 4. Press the SW1 switch again before the red LED turns off (before 1 second is elapsed) | Expected behavior is that the current LED turns off immediately and the next LED turn on for 1 second (next state) | Matches Expected Result | Pass